## Objectives Register
ENVIRONMENTAL OBJECTIVES REGISTER — CADILLAC HERTZ TEAM JOTA
Document Ref: ENV-OBJ-001 ¦ Version: 2.0 ¦ Date: May 2026 ¦ Owner: EMS Manager (Sustainability Manager)
Objective | Payback | Target | Status | Start Date | Target Date | Responsibility | Last Reviewed | Status Report / Notes
Reduce Carbon Footprint | Long | 5–10% reduction against 2025 Scope 3 baseline | On Target | 01/05/2025 | 31/12/2026 | Leadership Team | 17/03/2026 | First full Scope 3 GHG carbon footprint completed (2025 baseline). 4.2% reduction in Scope 1 & 2 (Q4 2023–Q3 2024 against Scope 2 baseline). WEC mandates 100% sustainable biofuel — actual CO₂e may be lower. Race car fuel correction: 2024 Scope 1 corrected to 91.53 tCO₂e; corrected 2024 total = 2,075.22 tCO₂e. VSME to be re-run before audit.
Improve Internal Training | Long | All staff trained; at least one documented environmental awareness toolbox talk delivered and evidenced before FIA audit | On Target — Action Required (Environmental Training) | 01/11/2024 | 31/12/2026 | HR Manager | 17/03/2026 | General staff training broadly up to date. Environmental-specific training not yet carried out. PRIORITY: Deliver and evidence a documented environmental awareness session (toolbox talk) covering significant aspects, objectives and responsibilities before the audit. Attendance record required.
Improve Infrastructure | Long | Most effective environmental controls in place; EV charging installed; operations relocated to energy-efficient facility | Achieved | 01/11/2024 | 31/12/2025 | Team Manager | 17/03/2026 | Achieved. EV charging infrastructure installed on site. Engineering operations relocated to newer, more energy-efficient premises. Final management review sign-off required to formally close this objective.
Zero Waste to Landfill & Increase Recycling | Medium | Zero landfill; all recyclables segregated; 5–10% increase in recycling rate | On Target | 01/11/2024 | 31/12/2026 | Leadership Team | 17/03/2026 | End 2025 – Feb 2026: 34.34% recycling rate (vs 23% Q1–Q3 2024). Zero waste to landfill maintained. Measured via Veolia customer hub and waste transfer notes. Rolling objective with no end date.
Energy Use | Long | 10% energy reduction across all operations by June 2026 against 2024 baseline | Review Required | 12/06/2025 | 12/06/2026 | All staff | 17/03/2026 | 2025 annual review not yet completed. Full year 2025 energy consumption data must be compiled and compared against 2024 baseline. Status report to be updated before FIA audit.
Water Consumption | Medium | 10% reduction in water consumption by June 2026 against baseline | Review Required | 12/06/2025 | 12/06/2026 | All staff | 17/03/2026 | 2025 annual review not yet completed. Full year 2025 water consumption data must be compiled and compared against baseline. Aerators on all taps and recycled water toilet systems under review.
Ground & Water Pollution Prevention | Medium | Zero hazardous spill incidents; complete annual spill scenario drill | On Target | 12/06/2025 | 12/06/2026 | All staff | 17/03/2026 | Zero hazardous spill incidents recorded through March 2026. Annual spill scenario drill to be scheduled and completed before audit. Chemical storage maintained in bunded containers.
Supply Chain Sustainability | Medium | Assess top suppliers' environmental credentials; document in Approved Supplier List | In Progress | 12/06/2025 | 12/06/2026 | Team Manager | 17/03/2026 | 16 suppliers tracked. ISO 14001 certified: 3 (Aero Tec, Euro Car Parts, RS Components). Environmental policy on file: 10/16. 4 awaiting response: FC Lane, Bosch, Michelin, Bridgestone. Baseline: 18.75% ISO 14001; 62.5% with env. policy.
Transport Emissions Reduction | Medium | 7.5% reduction in non-essential logistics transport weight (kg) against 2025/26 baseline | Review Required — Transport Log Not Yet Started | 12/06/2025 | 12/06/2026 | All staff | 17/03/2026 | No transport log data collected as at March 2026. Transport log recording weight of freight MUST be started immediately. At least one full quarter of data required before FIA audit. 2024 benchmark: ~1,085,112 tonne-miles total.
Biodiversity | Long | Continue to protect and have limited impact on local biodiversity | On Target | 12/06/2025 | 12/06/2026 | All staff | 17/03/2026 | Night-time light pollution controls maintained. Team continues to encourage local biodiversity. Biodiversity survey of local area to be confirmed as completed or scheduled before audit.
Enhance the EMS | Short | Compliant with all FIA 3-Star environmental requirements | On Target | 01/03/2025 | 31/03/2026 | EMS Manager (Sustainability Manager) | 17/03/2026 | Target date extended from Dec 2025 to Mar 2026. Open OFIs to close: KPI baselines (Cerquetti Dec 2024), Environmental Training, Significant Aspects communication, Legal Compliance Evaluation. On-site audit scheduled 28 May 2026.
VERSION HISTORY
Version | Date | Author | Summary of Changes
1.0 | March 2026 | EMS Manager | Initial Objectives Register issued as controlled document.
2.0 | May 2026 | EMS Manager | Status reports updated. Transport log gap flagged as action required. Environmental training noted as priority. Infrastructure objective closed as Achieved. Reissued with version history.